## Overview
90-Day Quantum Readiness Roadmap
Organization: | [Enter Organization Name] |  | Start Date: | [Enter Start Date] |  | End Date:
Phase Overview
Phase | Timeline | Key Objectives | Status | % Complete
Phase 1: Discovery | Weeks 1-4 | Inventory cryptographic assets, identify stakeholders, assess current state | Not Started | 0%
Phase 2: Analysis | Weeks 5-8 | Risk assessment, prioritization, vendor evaluation, roadmap development | Not Started | 0%
Phase 3: Planning | Weeks 9-12 | Migration planning, resource allocation, pilot preparation, governance setup | Not Started | 0%
Timeline Visualization
Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Phase 1: Discovery
Phase 2: Analysis
Phase 3: Planning
Key Milestones
Week | Milestone | Target Date | Actual Date | Status
Week 2 | Cryptographic inventory initiated |  |  | Pending
Week 4 | Initial risk assessment complete |  |  | Pending
Week 6 | Vendor PQC roadmaps collected |  |  | Pending
Week 8 | Priority systems identified |  |  | Pending
Week 10 | Migration roadmap drafted |  |  | Pending
Week 12 | Executive approval obtained |  |  | Pending

## Weekly Tasks
Weekly Task Breakdown
Week | Task | Owner | Due Date | Priority | Status | Notes
Week 1 | Kick-off meeting with stakeholders |  |  | High | Not Started
Week 1 | Define project scope and objectives |  |  | High | Not Started
Week 1 | Identify key systems for inventory |  |  | Medium | Not Started
Week 2 | Deploy cryptographic discovery tools |  |  | High | Not Started
Week 2 | Begin automated infrastructure scans |  |  | High | Not Started
Week 2 | Document key management systems |  |  | Medium | Not Started
Week 3 | Review custom application code |  |  | Medium | Not Started
Week 3 | Catalog third-party dependencies |  |  | Medium | Not Started
Week 3 | Interview application owners |  |  | Low | Not Started
Week 4 | Complete initial inventory |  |  | High | Not Started
Week 4 | Validate inventory completeness |  |  | Medium | Not Started
Week 4 | Present findings to stakeholders |  |  | High | Not Started
Week 5 | Classify data by sensitivity |  |  | High | Not Started
Week 5 | Identify HNDL-vulnerable systems |  |  | High | Not Started
Week 5 | Assess crypto-agility per system |  |  | Medium | Not Started
Week 6 | Request vendor PQC roadmaps |  |  | Medium | Not Started
Week 6 | Evaluate vendor timelines |  |  | Medium | Not Started
Week 6 | Document vendor gaps |  |  | Low | Not Started
Week 7 | Calculate risk scores |  |  | High | Not Started
Week 7 | Create risk heat map |  |  | Medium | Not Started
Week 7 | Prioritize migration order |  |  | High | Not Started
Week 8 | Complete risk assessment |  |  | High | Not Started
Week 8 | Present to leadership |  |  | High | Not Started
Week 8 | Obtain feedback and adjust |  |  | Medium | Not Started
Week 9 | Draft migration roadmap |  |  | High | Not Started
Week 9 | Define resource requirements |  |  | Medium | Not Started
Week 9 | Identify pilot systems |  |  | Medium | Not Started
Week 10 | Develop budget estimates |  |  | High | Not Started
Week 10 | Create staffing plan |  |  | Medium | Not Started
Week 10 | Define success metrics |  |  | Medium | Not Started
Week 11 | Design governance structure |  |  | Medium | Not Started
Week 11 | Draft policies and procedures |  |  | Medium | Not Started
Week 11 | Plan training programs |  |  | Low | Not Started
Week 12 | Finalize migration roadmap |  |  | High | Not Started
Week 12 | Present to executive sponsor |  |  | High | Not Started
Week 12 | Obtain budget approval |  |  | High | Not Started

## Resources
Resource Allocation
Team Members
Role | Name | Department | % Allocation | Start Week | End Week | Skills | Notes
Project Sponsor |  | Executive | 10% | 1 | 12
Project Manager |  | PMO | 100% | 1 | 12
Security Architect |  | Security | 50% | 1 | 12
Cryptography SME |  | Security | 75% | 1 | 12
Infrastructure Lead |  | IT Ops | 50% | 2 | 12
Application Developer |  | Development | 25% | 3 | 12
Compliance Officer |  | GRC | 25% | 1 | 12
Vendor Manager |  | Procurement | 25% | 5 | 8
Budget Allocation
Category | Estimated Cost | Actual Cost | Variance | Notes
Personnel (internal) | $0 | $0
Consulting/Advisory | $0 | $0
Discovery Tools | $0 | $0
Training | $0 | $0
Documentation | $0 | $0
Contingency (15%) |  | $0
TOTAL |  | $0

## Risk Tracking
Risk Register
ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner | Status
R1 | Incomplete cryptographic inventory | Technical | Medium | High |  | Deploy multiple discovery tools; manual code review |  | Open
R2 | Insufficient executive sponsorship | Governance | Low | High |  | Regular executive briefings; clear ROI communication |  | Open
R3 | Vendor PQC roadmap delays | Supply Chain | Medium | Medium |  | Early vendor engagement; alternative vendor identification |  | Open
R4 | Resource availability constraints | Operational | Medium | Medium |  | Early resource planning; cross-training |  | Open
R5 | Scope creep | Project | Medium | Medium |  | Clear scope definition; change control process |  | Open
R6 | Legacy system complexity | Technical | High | High |  | Phased approach; expert consultation |  | Open
R7 | Budget constraints | Financial | Low | Medium |  | Phased investment; ROI documentation |  | Open
R8 | Skill gaps in team | Operational | Medium | Medium |  | Training program; external expertise |  | Open
Risk Score Legend
1-2 | Low
3-4 | Medium
6-9 | High